## Sprint1
| Project Name: | Xây dựng website cho thuê xe
| Module Name: | Sprint 1
| Development Team: | STX
| Start Date: | 2019-03-06
| End Date: | 2020-03-28
| SPRINT 1 REPORT | [7 empty] | End task
| No. | Member Name | Actual | Estimate |  |  |  |  | Over time
| 1 | Lương Văn Trung | 44.4 | 41.4 |  |  |  |  | Late
| 2 | Võ Văn Phước | 48.4 | 41.4 |  |  |  |  | Behind schedule
| 3 | Nguyễn Xuân Trin | 23.0667 | 23.0667 |  |  |  |  | Ahead of schedule
| 4 | Phạm Chí Thiện | 24.0667 | 26.0667
| 5 | Huỳnh Công Thẩm | 26.0667 | 26.0667
| Total |  | 166 | 158
Sprint | Component | Task Name | PIC |  | Estimate | 2020-03-06 | 2020-03-07 | 2020-03-08 | 2020-03-09 | 2020-03-10 | 2020-03-11 | 2020-03-12 | 2020-03-13 | 2020-03-14 | 2020-03-15 | 2020-03-16 | 2020-03-17 | 2020-03-18 | 2020-03-19 | 2020-03-20 | 2020-03-21 | 2020-03-22 | 2020-03-23 | 2020-03-24 | 2020-03-25 | 2020-03-26 | 2020-03-27 | 2020-03-28 | 2020-03-29
1 | Sprint Planning Meeting |  | Team |  | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tạo Sprint Backlog |  | Trung |  | 8 | 8 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tạo Database |  | Phước |  | 8 | 8 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tạo Test Plan document cho Sprint 1 |  | Team Test |  | 8 | 8 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Design User Interface | Design user interface "Đăng nhập" | Trung |  | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Design user interface "Đăng ký" | Trung |  | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Design user interface "Trang chủ tìm xe" | Phước |  | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Design user interface "Đặt xe" | Phước |  | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Design user interface "Quản lý xe của đại lý" | Phước |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Design user interface "Thêm xe của đại lý" | Trung |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Design Test Case | Design test case "Đăng nhập" | Trin |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Design test case "Đăng ký" | Trin |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Design test case "Trang chủ tìm xe" | Thiện |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Design test case "Đặt xe" | Thiện |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Design test case "Quản lý xe của đại lý" | Thẩm |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Design test case "Thêm xe của đại lý" | Thẩm |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Code | Code chức năng "Đăng nhập" | Trung |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Code chức năng "Đăng ký" | Trung |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Code chức năng "Trang chủ tìm xe" | Phước |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Code chức năng "Đặt xe" | Phước |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Code chức năng "Quản lý xe của đại lý" | Phước |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Code chức năng "Thêm xe của đại lý" | Trung |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Test | Test "Đăng nhập " | Trin |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Test "Đăng ký " | Trin |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Test "Trang chủ tìm xe" | Thiện |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Test "Đặt xe" | Thiện |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Test "Quản lý xe của đại lý" | Thẩm |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Test "Thêm xe của đại lý" | Thẩm |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Fix bugs | Fix bugs "Đăng nhập " | Trung |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
|  | Fix bugs "Đăng ký " | Trung |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
|  | Fix bugs "Trang chủ tìm xe" | Phước |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
|  | Fix bugs "Đặt xe" | Phước |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
|  | Fix bugs "Quản lý xe của đại lý" | Phước |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
|  | Fix bugs "Thêm xe của đại lý" | Trung |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0
| Re-test | Re-test "Đăng nhập " | Trin |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
|  | Re-test "Đăng ký " | Trin |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
|  | Re-test "Trang chủ tìm xe" | Thiện |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0
|  | Re-test "Đặt xe" | Thiện |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
|  | Re-test "Quản lý xe của đại lý" | Thẩm |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
|  | Re-test "Thêm xe của đại lý" | Thẩm |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0
| Release Sprint 1 | Sprint 1 Review Meeting | Team |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0
|  | Sprint 2 Retrospective Meeting | Team |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  |  | Esimate |  | 158 | 158 | 154 | 142 | 130 | 123 | 117 | 110 | 110 | 101 | 92 | 85 | 78 | 71 | 64 | 64 | 57 | 43 | 36 | 29 | 22 | 15 | 8 | 4 | 0
Sprint | Component | Task Name | PIC | Actual | Estimate | 2020-03-06 | 2020-03-07 | 2020-03-08 | 2020-03-09 | 2020-03-10 | 2020-03-11 | 2020-03-12 | 2020-03-13 | 2020-03-14 | 2020-03-15 | 2020-03-16 | 2020-03-17 | 2020-03-18 | 2020-03-19 | 2020-03-20 | 2020-03-21 | 2020-03-22 | 2020-03-23 | 2020-03-24 | 2020-03-25 | 2020-03-26 | 2020-03-27 | 2020-03-28 | 2020-03-29
1 | Sprint Plan Meeting |  | Team | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Create Sprint Backlog |  | Trung | 8 | 8 | 8 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tạo Database |  | Phước | 10 | 8 | 8 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2
| Tạo Test Plan document cho Sprint 1 |  | Team Test | 8 | 8 | 8 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Design User Interface | Design user interface "Đăng nhập" | Trung | 4 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1
|  | Design user interface "Đăng ký" | Trung | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1
|  | Design user interface "Trang chủ tìm xe" | Phước | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Design user interface "Đặt xe" | Phước | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1
|  | Design user interface "Quản lý xe của đại lý" | Phước | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1
|  | Design user interface "Thêm xe của đại lý" | Trung | 6 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2
| Design Test Case | Design test case "Đăng nhập" | Trin | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1
|  | Design test case "Đăng ký" | Trin | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1
|  | Design test case "Trang chủ tìm xe" | Thiện | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
-1
|  | Design test case "Đặt xe" | Thiện | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1
|  | Design test case "Quản lý xe của đại lý" | Thẩm | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1
|  | Design test case "Thêm xe của đại lý" | Thẩm | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Code | Code chức năng "Đăng nhập" | Trung | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1
|  | Code chức năng "Đăng ký" | Trung | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1
|  | Code chức năng "Trang chủ tìm xe" | Phước | 8 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2
|  | Code chức năng "Đặt xe" | Phước | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1
|  | Code chức năng "Quản lý xe của đại lý" | Phước | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1
|  | Code chức năng "Thêm xe của đại lý" | Trung | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Test | Test "Đăng nhập" | Trin | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
-1
|  | Test "Đăng ký" | Trin | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
-1
|  | Test "Trang chủ tìm xe" | Thiện | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
-1
|  | Test "Đặt xe" | Thiện | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Test "Quản lý xe của đại lý" | Thẩm | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Test "Thêm xe của đại lý" | Thẩm | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
-1
| Fixing bugs | Fix bugs "Đăng nhập" | Trung | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
-1
|  | Fix bugs "Đăng ký" | Trung | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
-1
|  | Fix bugs "Trang chủ tìm xe" | Phước | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
-1
|  | Fix bugs "Đặt xe" | Phước | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
|  | Fix bugs "Quản lý xe của đại lý" | Phước | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
|  | Fix bugs "Thêm xe của đại lý" | Trung | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0
-1
| Re-testing | Re-test "Đăng nhập" | Trin | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
|  | Re-test "Đăng ký" | Trin | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
|  | Re-test "Trang chủ tìm xe" | Thiện | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0
|  | Re-test "Đặt xe" | Thiện | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
-1
|  | Re-test "Quản lý xe của đại lý" | Thẩm | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
-1
|  | Re-test "Thêm xe của đại lý" | Thẩm | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0
1
| Release Sprint 1 | Sprint 1 Review Meeting | Team | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0
|  | Sprint 1 Retrospective Meeting | Team | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  |  | Actual |  | 166 | 158 | 143 | 135 | 132 | 124 | 119 | 113 | 104 | 97 | 94 | 85 | 78 | 73 | 65 | 57 | 49 | 38 | 35 | 26 | 21 | 14 | 8 | 4 | 0
|  |  | Esimate |  | 158 | 158 | 154 | 142 | 130 | 123 | 117 | 110 | 110 | 101 | 92 | 85 | 78 | 71 | 64 | 64 | 57 | 43 | 36 | 29 | 22 | 15 | 8 | 4 | 0

## Sprint2
| Project Name: | Xây dựng website cho thuê xe
| Module Name: | Sprint 2
| Development Team: | STX
| Start Date: | 2019-03-29
| End Date: | 2020-04-26
| SPRINT 1 REPORT | [7 empty] | End task
| No. | Member Name | Actual | Estimate |  |  |  |  | Over time
| 1 | Lương Văn Trung | 55.4 | 58.4 |  |  |  |  | Late
| 2 | Võ Văn Phước | 58.4 | 66.4 |  |  |  |  | Behind schedule
| 3 | Nguyễn Xuân Trin | 27.0667 | 33.0667 |  |  |  |  | Ahead of schedule
| 4 | Phạm Chí Thiện | 20.0667 | 23.0667
| 5 | Huỳnh Công Thẩm | 21.0667 | 23.0667
| Total |  | 182 | 204
Sprint | Component | Task Name | PIC |  | Estimate | 2020-03-29 | 2020-03-30 | 2020-03-31 | 2020-04-01 | 2020-04-02 | 2020-04-03 | 2020-04-04 | 2020-04-05 | 2020-04-06 | 2020-04-07 | 2020-04-08 | 2020-04-09 | 2020-04-10 | 2020-04-11 | 2020-04-12 | 2020-04-13 | 2020-04-14 | 2020-04-15 | 2020-04-16 | 2020-04-17 | 2020-04-18 | 2020-04-19 | 2020-04-20 | 2020-04-21 | 2020-04-22 | 2020-04-23 | 2020-04-24 | 2020-04-25 | 2020-04-26 | 2020-04-27
2 | Sprint Planning Meeting |  | Team |  | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tạo Sprint Backlog |  | Trung |  | 8 | 8 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tạo Test Plan document cho Sprint 2 |  | Team Test |  | 8 | 8 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Design User Interface | Design user interface "Lịch sử thuê xe" | Phước |  | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Design user interface " Quản lí bài viết” | Trung |  | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Design user interface "Sửa thông tin xe của đại lý" | Phước |  | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Design user interface "Lịch sử giao dịch xe" | Trung |  | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Design user interface " Quản lí các đại lý là thành viên" | Phước |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Design user interface "Chi tiết đơn thuê xe” | Trung |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Design user interface "Xem lịch sử giao dịch từng xe của đại lý" | Phước |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Design Test Case | Design test case " Lịch sử thuê xe " | Trin |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Design test case " Quản lí bài viết " | Thiện |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Design test case " Sửa thông tin xe của đại lý " | Thẩm |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Design test case " Lịch sử giao dịch xe " | Trin |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Design test case " Quản lí các đại lý là thành viên (Admin)" | Thiện |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Design test " Chi tiết đơn thuê xe” | Thẩm |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Design test case " Xem lịch sử giao dịch từng xe của đại lý " | Trin |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Code | Code chức năng " Lịch sử thuê xe " | Phước |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Code chức năng " Quản lí bài viết " | Trung |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Code chức năng " Sửa thông tin xe của đại lý " | Phước |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Code chức năng " Lịch sử giao dịch xe " | Trung |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Code chức năng " Quản lí các đại lý là thành viên (Admin)" | Phước |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Code chức năng " Chi tiết đơn thuê xe” | Trung |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Code chức năng " Xem lịch sử giao dịch từng xe của đại lý " | Phước |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Test | Test " Lịch sử thuê xe " | Trin |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Test chức năng " Quản lí bài viết " | Thiện |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Test " Sửa thông tin xe của đại lý " | Thẩm |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Test chức năng " Lịch sử giao dịch xe " | Trin |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Test chức năng " Quản lí các đại lý là thành viên (Admin)" | Thiện |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Test " Chi tiết đơn thuê xe” | Thẩm |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Test " Xem lịch sử giao dịch từng xe của đại lý " | Trin |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Fix bugs | Fix bugs " Lịch sử thuê xe " | Phước |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Fix bugs " Quản lí bài viết " | Trung |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Fix bugs " Sửa thông tin xe của đại lý " | Phước |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0
|  | Fix bugs " Lịch sử giao dịch xe " | Trung |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0
|  | Fix bugs " Quản lí các đại lý là thành viên (Admin)" | Phước |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0
|  | Fix bugs " Chi tiết đơn thuê xe” | Trung |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0
|  | Fix bugs " Xem lịch sử giao dịch từng xe của đại lý " | Phước |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0
| Re-test | Re-test " Lịch sử thuê xe " | Trin |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
|  | Re-test " Quản lí bài viết " | Thiện |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
|  | Re-test " Sửa thông tin xe của đại lý " | Thẩm |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
|  | Re-test " Lịch sử giao dịch xe " | Trin |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
|  | Re-test " Quản lí các đại lý là thành viên (Admin)" | Thiện |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
|  | Re-test " Chi tiết đơn thuê xe” | Thẩm |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
|  | Re-test " Xem lịch sử giao dịch từng xe của đại lý " | Trin |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0
| Release Sprint 2 | Sprint 2 Review Meeting | Team |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0
|  | Sprint 2 Retrospective Meeting | Team |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  |  | Esimate |  | 204 | 204 | 194 | 188 | 184 | 176 | 168 | 160 | 156 | 147 | 138 | 134 | 126 | 118 | 114 | 106 | 102 | 94 | 82 | 78 | 78 | 66 | 54 | 50 | 42 | 34 | 26 | 22 | 10 | 4 | 0
Sprint | Component | Task Name | PIC | Actual | Estimate | 2020-03-29 | 2020-03-30 | 2020-03-31 | 2020-04-01 | 2020-04-02 | 2020-04-03 | 2020-04-04 | 2020-04-05 | 2020-04-06 | 2020-04-07 | 2020-04-08 | 2020-04-09 | 2020-04-10 | 2020-04-11 | 2020-04-12 | 2020-04-13 | 2020-04-14 | 2020-04-15 | 2020-04-16 | 2020-04-17 | 2020-04-18 | 2020-04-19 | 2020-04-20 | 2020-04-21 | 2020-04-22 | 2020-04-23 | 2020-04-24 | 2020-04-25 | 2020-04-26 | 2020-04-27
2 | Sprint Plan Meeting |  | Team | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Create Sprint Backlog |  | Trung | 8 | 8 | 8 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tạo Test Plan document cho Sprint 2 |  | Team Test | 8 | 8 | 8 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Design User Interface | Design user interface "Lịch sử thuê xe" | Phước | 3 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
-1
|  | Design user interface " Quản lí bài viết” | Trung | 3 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
-1
|  | Design user interface "Sửa thông tin xe của đại lý" | Phước | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1
|  | Design user interface "Lịch sử giao dịch xe" | Trung | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1
|  | Design user interface " Quản lí các đại lý là thành viên" | Phước | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
-1
|  | Design user interface "Chi tiết đơn thuê xe” | Trung | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1
|  | Design user interface "Xem lịch sử giao dịch từng xe của đại lý" | Phước | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
-1
| Design Test Case | Design test case " Lịch sử thuê xe " | Trin | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
-2
|  | Design test case " Quản lí bài viết " | Thiện | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
-1
|  | Design test case " Sửa thông tin xe của đại lý " | Thẩm | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1
|  | Design test case " Lịch sử giao dịch xe " | Trin | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
-1
|  | Design test case " Quản lí các đại lý là thành viên (Admin)" | Thiện | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1
|  | Design test " Chi tiết đơn thuê xe” | Thẩm | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1
|  | Design test case " Xem lịch sử giao dịch từng xe của đại lý " | Trin | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1
| Code | Code chức năng " Lịch sử thuê xe " | Phước | 10 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2
|  | Code chức năng " Quản lí bài viết " | Trung | 10 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2
|  | Code chức năng " Sửa thông tin xe của đại lý " | Phước | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Code chức năng " Lịch sử giao dịch xe " | Trung | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Code chức năng " Quản lí các đại lý là thành viên (Admin)" | Phước | 6 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
-2
|  | Code chức năng " Chi tiết đơn thuê xe” | Trung | 6 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
-2
|  | Code chức năng " Xem lịch sử giao dịch từng xe của đại lý " | Phước | 6 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
-2
| Test | Test " Lịch sử thuê xe " | Trin | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
-2
|  | Test chức năng " Quản lí bài viết " | Thiện | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
-2
|  | Test " Sửa thông tin xe của đại lý " | Thẩm | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
-1
|  | Test chức năng " Lịch sử giao dịch xe " | Trin | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
-1
|  | Test chức năng " Quản lí các đại lý là thành viên (Admin)" | Thiện | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Test " Chi tiết đơn thuê xe” | Thẩm | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
-2
|  | Test " Xem lịch sử giao dịch từng xe của đại lý " | Trin | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
-1
| Fixing bugs | Fix bugs " Lịch sử thuê xe " | Phước | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
-1
|  | Fix bugs " Quản lí bài viết " | Trung | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
-2
|  | Fix bugs " Sửa thông tin xe của đại lý " | Phước | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0
-1
|  | Fix bugs " Lịch sử giao dịch xe " | Trung | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0
-1
|  | Fix bugs " Quản lí các đại lý là thành viên (Admin)" | Phước | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0
-1
|  | Fix bugs " Chi tiết đơn thuê xe” | Trung | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0
-1
|  | Fix bugs " Xem lịch sử giao dịch từng xe của đại lý " | Phước | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0
-1
| Re-testing | Re-test " Lịch sử thuê xe " | Trin | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
|  | Re-test " Quản lí bài viết " | Thiện | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
|  | Re-test " Sửa thông tin xe của đại lý " | Thẩm | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
|  | Re-test " Lịch sử giao dịch xe " | Trin | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
|  | Re-test " Quản lí các đại lý là thành viên (Admin)" | Thiện | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
-1
|  | Re-test " Chi tiết đơn thuê xe” | Thẩm | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
-1
|  | Re-test " Xem lịch sử giao dịch từng xe của đại lý " | Trin | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0
| Release Sprint 2 | Sprint 2 Review Meeting | Team | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0
|  | Sprint 2 Retrospective Meeting | Team | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  |  | Actual |  | 182 | 204 | 194 | 186 | 184 | 174 | 170 | 160 | 155 | 145 | 139 | 135 | 125 | 122 | 114 | 106 | 102 | 96 | 78 | 76 | 78 | 61 | 51 | 49 | 39 | 32 | 24 | 21 | 8 | 4 | 0
|  |  | Esimate |  | 204 | 204 | 194 | 188 | 184 | 176 | 168 | 160 | 156 | 147 | 138 | 134 | 126 | 118 | 114 | 106 | 102 | 94 | 82 | 78 | 78 | 66 | 54 | 50 | 42 | 34 | 26 | 22 | 10 | 4 | 0

## Sprint3
| Project Name: | Xây dựng website cho thuê xe
| Module Name: | Sprint 3
| Development Team: | STX
| Start Date: | 2019-04-27
| End Date: | 2020-05-14
| SPRINT 1 REPORT | [7 empty] | End task
| No. | Member Name | Actual | Estimate |  |  |  |  | Over time
| 1 | Lương Văn Trung | 34.4 | 34.4 |  |  |  |  | Late
| 2 | Võ Văn Phước | 40.4 | 34.4 |  |  |  |  | Behind schedule
| 3 | Nguyễn Xuân Trin | 20.0667 | 18.0667 |  |  |  |  | Ahead of schedule
| 4 | Phạm Chí Thiện | 22.0667 | 19.0667
| 5 | Huỳnh Công Thẩm | 16.0667 | 15.0667
| Total |  | 133 | 121
Sprint | Component | Task Name | PIC |  | Estimate | 2020-04-27 | 2020-04-28 | 2020-04-29 | 2020-05-02 | 2020-05-03 | 2020-05-04 | 2020-05-05 | 2020-05-06 | 2020-05-07 | 2020-05-08 | 2020-05-09 | 2020-05-10 | 2020-05-11 | 2020-05-12 | 2020-05-13 | 2020-05-14 | 2020-05-15
3 | Sprint Planning Meeting |  | Team |  | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tạo Sprint Backlog |  | Trung |  | 8 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tạo Test Plan document cho Sprint 3 |  | Team Test |  | 8 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Design User Interface | Design user interface " Quản lí xe (Admin)” | Phước |  | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Design user interface "Thống Kê của đại lý" | Trung |  | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Design user interface "Thống Kê của Admin" | Trung |  | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Design user interface "Thanh toán của người dùng" | Phước |  | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Design Test Case | Design test " Quản lí xe (Admin)” | Thẩm |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Design test case " Thống Kê của đại lý " | Thiện |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Design test case " Thống Kê của Admin " | Thiện |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Design test case " Thanh toán của người dùng" | Trin |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Code | Code chức năng " Quản lí xe (Admin)” | Phước |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Code chức năng " Thống Kê của đại lý " | Trung |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Code chức năng " Thống Kê của Admin " | Trung |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Code chức năng "Thanh toán của người dùng" | Phước |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Test | Test " Quản lí xe (Admin)” | Thẩm |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0
|  | Test chức năng " Thống Kê của đại lý " | Thiện |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
|  | Test chức năng " Thống Kê của Admin " | Thiện |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
|  | Test chức năng " Thanh toán của người dùng " | Trin |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0
| Fix bugs | Fix bugs " Quản lí xe (Admin)” | Phước |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
|  | Fix bugs " Thống Kê của đại lý " | Trung |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
|  | Fix bugs " Thống Kê của Admin " | Trung |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
|  | Fix bugs " Thanh toán của người dùng " | Phước |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
| Re-test | Re-test " Quản lí xe (Admin)” | Thẩm |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0
|  | Re-test " Thống Kê của đại lý " | Thiện |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
|  | Re-test " Thống Kê của Admin " | Thiện |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
|  | Re-test " Thanh toán của người dùng " | Trin |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0
| Release Sprint 3 | Sprint 3 Review | Team |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0
|  | Sprint 3 Retrospective Meeting | Team |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  |  | Esimate |  | 121 | 121 | 109 | 101 | 101 | 89 | 77 | 71 | 56 | 48 | 44 | 40 | 29 | 26 | 18 | 8 | 4 | 0
Sprint | Component | Task Name | PIC | Actual | Estimate | 2020-04-27 | 2020-04-28 | 2020-04-29 | 2020-05-02 | 2020-05-03 | 2020-05-04 | 2020-05-05 | 2020-05-06 | 2020-05-07 | 2020-05-08 | 2020-05-09 | 2020-05-10 | 2020-05-11 | 2020-05-12 | 2020-05-13 | 2020-05-14 | 2020-05-15
3 | Sprint Plan Meeting |  | Team | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Create Sprint Backlog |  | Trung | 8 | 8 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tạo Test Plan document cho Sprint 3 |  | Team Test | 8 | 8 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Design User Interface | Design user interface " Quản lí xe (Admin)” | Phước | 4 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
-2
|  | Design user interface "Thống Kê của đại lý" | Trung | 4 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
-2
|  | Design user interface "Thống Kê của Admin" | Trung | 4 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
-2
|  | Design user interface "Thanh toán của người dùng" | Phước | 8 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2
| Design Test Case | Design test case " Quản lí xe (Admin)” | Thẩm | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1
|  | Design test case " Thống Kê của đại lý " | Thiện | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Design test case " Thống Kê của Admin " | Thiện | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1
|  | Design test case " Thanh toán của người dùng" | Trin | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1
| Code | Code chức năng " Quản lí xe (Admin)” | Phước | 10 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2
|  | Code chức năng " Thống Kê của đại lý " | Trung | 6 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2
|  | Code chức năng " Thống Kê của Admin " | Trung | 6 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2
|  | Code chức năng "Thanh toán của người dùng" | Phước | 10 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2
| Test | Test " Quản lí xe (Admin)” | Thẩm | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0
1
|  | Test chức năng " Thống Kê của đại lý " | Thiện | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
1
|  | Test chức năng " Thống Kê của Admin " | Thiện | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
1
|  | Test chức năng " Thanh toán của người dùng " | Trin | 7 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0
1
| Fixing bugs | Fix bugs " Quản lí xe (Admin)” | Phước | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
1
|  | Fix bugs " Thống Kê của đại lý " | Trung | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
|  | Fix bugs " Thống Kê của Admin " | Trung | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
|  | Fix bugs " Thanh toán của người dùng " | Phước | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
1
| Re-testing | Re-test " Quản lí xe (Admin)” | Thẩm | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0
1
|  | Re-test " Thống Kê của đại lý " | Thiện | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
|  | Re-test " Thống Kê của Admin " | Thiện | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
|  | Re-test " Thanh toán của người dùng " | Trin | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0
| Release Sprint 3 | Sprint 3 Review Meeting | Team | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0
|  | Sprint 3 Retrospective Meeting | Team | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  |  | Actual |  | 133 | 121 | 107 | 101 | 93 | 87 | 77 | 72 | 58 | 52 | 41 | 42 | 32 | 27 | 20 | 9 | 4 | 0
|  |  | Esimate |  | 121 | 121 | 109 | 101 | 101 | 89 | 77 | 71 | 56 | 48 | 44 | 40 | 29 | 26 | 18 | 8 | 4 | 0

## Report
SPRINT BACKLOG REPORT
| Trung |  | Phước |  | Trin |  | Thiện |  | Thẩm |  | FINAL TOTAL
| Actual | Estimate | Actual | Estimate | Actual | Estimate | Actual | Estimate | Actual | Estimate | Actual | Estimate
Sprint 1 | 44.4 | 41.4 | 48.4 | 41.4 | 23.0667 | 23.0667 | 24.0667 | 26.0667 | 26.0667 | 26.0667 | 166 | 158
Sprint 2 | 55.4 | 58.4 | 58.4 | 66.4 | 27.0667 | 33.0667 | 20.0667 | 23.0667 | 21.0667 | 23.0667 | 182 | 204
Sprint 3 | 34.4 | 34.4 | 40.4 | 34.4 | 20.0667 | 18.0667 | 22.0667 | 19.0667 | 16.0667 | 15.0667 | 133 | 121
Total | 134.2 | 134.2 | 147.2 | 142.2 | 70.2 | 74.2 | 66.2 | 68.2 | 63.2 | 64.2 | 481 | 483

## Sheet2 (hidden)
STT | Tên | Ngày bắt đầu | Ngày kết thúc | Thời gian ước tính | Tên thành viên
1 | Initial | 2016-08-01 | 2016-08-04 | 16
1.1 | Tổng hợp yêu cầu | 21-02-2017 | 2017-05-03 | 8 | Tân, Quý, Linh
1.2 | Viết tài liệu Proposal | 2017-07-03 | 2017-08-03 | 8 | Tân, Quý
2 | Start Up | 2017-08-03 | 17-03-2017 | 92
2.1 | Project’s Meeting | 2017-08-03 | 2017-08-23 | 8 | Tân, Quý, Linh
2.2 | Viết tài liệu User Stories | 2017-08-03 | 2017-10-03 | 24 | Tân, Quý, Linh
2.3 | Viết tài liệu Product Backlog | 2017-09-03 | 2017-10-03 | 12 | Tân, Quý, Linh
2.4 | Review Document | 2017-11-03 | 2017-11-03 | 8 | Tân, Quý, Linh
2.5 | Create Project Plan Document | 13-03-2017 | 15-03-2017 | 24 | Tân, Quý, Linh
2.6 | Review Document | 16-03-2017 | 2016-08-16 | 8 | Tân, Quý, Linh
2.8 | Review Document | 17-03-2017 | 17-03-2017 | 8 | Tân, Quý, Linh
3 | Development | 17-03-2017 | 2017-10-05 | 518
3.1 | Sprint 1 | 17-03-2017 | 2017-02-04 | 148
3.1.1 | Sprint Planning Meeting | 17-03-2017 | 17-03-2017 | 8 | Tân, Quý, Linh
3.1.2 | Tạo Sprint Backlog | 17-03-2017 | 17-03-2017 | 4 | Tân
3.1.3 | Tạo Test Plan document cho Sprint 1 | 18-03-2017 | 18-03-2017 | 4 | Linh
3.1.5 | Design user interface | 24-03-2017 | 26-03-2017 | 12
3.1.5.1 | Design user interface of “Nhập văn bản bằng tay” | 24-03-2017 | 24-03-2017 | 8 | Quý
3.1.5.2 | Design user interface of “Nhập văn bản từ file” | 25-03-2017 | 25-03-2017 | 4 | Linh
3.1.6 | Design Test case for: | 26-03-2017 | 26-03-2017 | 16
3.1.6.1 | Design test case cho chức năng “ Nhập văn bản bằng tay ” | 26-03-2017 | 26-03-2017 | 4 | Linh
3.1.6.2 | Design test case cho chức năng “ Nhập văn bản từ file ” | 26-03-2017 | 26-03-2017 | 4 | Tân
3.1.6.3 | Design test case cho chức năng “Tách câu từ văn bản đầu vào” | 26-03-2017 | 26-03-2017 | 4 | Quý
3.1.6.4 | Design test case cho chức năng “Tách câu thành từ” | 26-03-2017 | 26-03-2017 | 4 | Tân
3.1.7 | Coding | 27-03-2017 | 28-03-2017 | 24
3.1.7.1 | Code chức năng “ Nhập văn bản bằng tay ” | 27-03-2017 | 27-03-2017 | 4 |  | Quý
3.1.7.2 | Code chức năng “Nhập văn bản từ file” | 27-03-2017 | 27-03-2017 | 4 |  | Linh
3.1.7.3 | Code chức năng “Tách câu từ văn bản đầu vào” | 27-03-2017 | 27-03-2017 | 8 |  | Tân
3.1.7.4 | Code chức năng “Tách câu thành từ” | 28-03-2017 | 28-03-2017 | 8 |  | Linh
3.1.8 | Testing | 29-03-2017 | 29-03-2017 | 16
3.1.8.1 | Test “ Nhập văn bản bằng tay ” | 29-03-2017 | 29-03-2017 | 4 |  | Linh
3.1.8.2 | Test “ Nhập văn bản từ file ” | 29-03-2017 | 29-03-2017 | 4 |  | Tân
3.1.8.3 | Test “ Tách câu từ văn bản đầu vào” | 29-03-2017 | 29-03-2017 | 4 |  | Quý
3.1.8.4 | Test “Tách câu thành từ” | 29-03-2017 | 29-03-2017 | 4 |  | Tân
3.1.9 | Fix bugs | 30-03-2017 | 30-03-2017 | 24
3.1.9.1 | Fix bugs “ Nhập văn bản bằng tay ” | 30-03-2017 | 30-03-2017 | 4 |  | Quý
3.1.9.2 | Fix bugs “ Nhập văn bản từ file ” | 30-03-2017 | 30-03-2017 | 4 |  | Linh
3.1.9.3 | Fix bugs “Tách câu từ văn bản đầu vào” | 30-03-2017 | 30-03-2017 | 8 |  | Tân
3.1.9.4 | Fix bugs “Tách câu thành từ” | 30-03-2017 | 30-03-2017 | 8 |  | Linh
3.1.10 | Re-testing | 31-03-2017 | 31-03-2017 | 24
3.1.10.1 | Re-test “Nhập văn bản bằng tay” | 31-03-2017 | 31-03-2017 | 4 |  | Linh
3.1.10.2 | Re-test “Nhập văn bản từ file” | 31-03-2017 | 31-03-2017 | 4 |  | Tân
3.1.10.3 | Re-test “Tách câu từ văn bản đầu vào” | 31-03-2017 | 31-03-2017 | 8 |  | Quý
3.1.10.4 | Re-test “Tách câu thành từ” | 31-03-2017 | 31-03-2017 | 8 |  | Tân
3.1.11 | Release Sprint 1: | 2017-01-04 | 2017-02-04 | 16
3.1.11.1 | Sprint 1 Review Meeting | 2017-01-04 | 2017-01-04 | 8 |  | Tân, Quý, Linh
3.1.11.2 | Sprint 1 Retrospective | 2017-02-04 | 2017-02-04 | 8 |  | Tân, Quý, Linh
3.2 | Sprint 2 | 2017-07-04 | 2017-05-05 | 370
3.2.1 | Sprint Planning Meeting | 2017-07-04 | 2017-07-04 | 8 |  | Tân, Quý, Linh
3.2.2 | Tạo Sprint Backlog Document | 2017-07-04 | 2017-07-04 | 4 |  | Tân
3.2.3 | Tạo Test Plan document cho Sprint 2 | 2017-08-04 | 2017-08-04 | 8 |  | Tân
3.2.5 | Design User Interface | 13-04-2017 | 14-04-2017 | 24
3.2.5.1 | Design user interface "Xem văn bản sau khi rút gọn" | 13-04-2017 | 13-04-2017 | 4 |  | Linh
3.2.5.2 | Design user interface “Lưu văn bản sau khi rút gọn” | 13-04-2017 | 13-04-2017 | 4 |  | Quý
3.2.5.3 | Design user interface of "Xem đồ thị liên kết giữa các câu" | 13-04-2017 | 13-04-2017 | 4 |  | Tân
3.2.5.4 | Design user interface “ Tùy chỉnh kích thước rút gọn văn bản” | 14-04-2017 | 14-04-2017 | 4 |  | Tân
3.2.5.5 | Design user interface “Xem tỉ lệ xếp hạng của các câu” | 14-04-2017 | 14-04-2017 | 4 |  | Quý
3.2.5.6 | Design user interface “Tìm kiếm nội dụng văn bản” | 14-04-2017 | 14-04-2017 | 4 |  | Linh
3.2.6 | Design Test Case: | 15-04-2017 | 17-04-2017 | 40
3.2.6.1 | Design test case for " Xem văn bản sau khi rút gọn " | 15-04-2017 | 15-04-2017 | 4 |  | Linh
3.2.6.2 | Design test case for “Xuất văn bản sau khi rút gọn ” | 15-04-2017 | 15-04-2017 | 4 |  | Quý
3.2.6.3 | Design test case for “ Xem đồ thị liên kết giữa các câu ” | 15-04-2017 | 15-04-2017 | 4 |  | Tân
3.2.6.4 | Design test case for “ Tùy chỉnh kích thước rút gọn văn bản ” | 16-04-2017 | 16-04-2017 | 4 |  | Tân
3.2.6.5 | Design test case for “ Xem tỉ lệ xếp hạng của các câu ” | 16-04-2017 | 16-04-2017 | 4 |  | Quý
3.2.6.6 | Design test case for “ Tìm kiếm nội dụng văn bản ” | 16-04-2017 | 16-04-2017 | 4 |  | Linh
3.2.6.7 | Design test case for “Tính độ liên kết giữa các câu” | 17-04-2017 | 17-04-2017 | 4 |  | Quý
3.2.6.8 | Design tesst case for “Tính độ ưu tiên giữa các câu tách ra” | 17-04-2017 | 17-04-2017 | 4 |  | Tân
3.2.6.9 | Design tesst case for “Tạo node đồ thị” | 17-04-2017 | 17-04-2017 | 4 |  | Linh
3.2.6.10 | Design tesst case for “Liên kết đồ thị” | 17-04-2017 | 17-04-2017 | 4 |  | Quý
3.2.7 | Coding: | 18-04-2017 | 26-04-2017 | 132
3.2.7.1 | Code chức năng “Tính độ liên kết giữa các câu” | 18-04-2017 | 19-04-2017 | 12 |  | Linh
3.2.7.2 | Code chức năng “Tính độ ưu tiên giữa các câu tách ra” | 18-04-2017 | 19-04-2017 | 12 |  | Quý
3.2.7.3 | Code chức năng “Tạo node cho đồ thị” | 18-04-2017 | 19-04-2017 | 12 |  | Tân
3.2.7.4 | Code chức năng “Liên kết đồ thị” | 19-04-2017 | 20-04-2017 | 12 |  | Tân
3.2.7.5 | Code chức năng “Tùy chỉnh kích thước rút gọn” | 20-04-2017 | 21-04-2017 | 12 |  | Linh
3.2.7.6 | Code chức năng “Xem văn bản sau khi rút gọn” | 20-04-2017 | 21-04-2017 | 12 |  | Quý
3.2.7.7 | Code chức năng “ Xem đồ thị liên kết giữa các câu” | 20-04-2017 | 24-04-2017 | 20 |  | Tân
3.2.7.8 | Code chức năng “Lưu văn bản sau khi rút gọn ” | 25-04-2017 | 26-04-2017 | 12 |  | Tân
3.2.7.9 | Code chức năng “ Xem tỉ lệ xếp hạng của các câu ” | 22-04-2017 | 26-04-2017 | 16 |  | Quý
3.2.7.10 | Code chức năng “ Tìm kiếm nội dụng văn bản” | 22-04-2017 | 26-04-2017 | 12 |  | Linh
3.2.8 | Testing: | 27-04-2017 | 28-04-2017 | 40
3.2.8.1 | Test " Xem văn bản sau khi rút gọn " | 27-04-2017 | 27-04-2017 | 4 |  | Quý
3.2.8.2 | Test “ Xuất văn bản sau khi rút gọn ” | 27-04-2017 | 27-04-2017 | 4 |  | Tân
3.2.8.3 | Test “ Xem đồ thị liên kết giữa các câu ” | 27-04-2017 | 27-04-2017 | 4 |  | Quý
3.2.8.4 | Test “ Tùy chỉnh kích thước rút gọn văn bản ” | 27-04-2017 | 27-04-2017 | 4 |  | Linh
3.2.8.5 | Test “ Xem tỉ lệ xếp hạng của các câu ” | 27-04-2017 | 27-04-2017 | 4 |  | Tân
3.2.8.6 | Test “ Tìm kiếm nội dụng văn bản ” | 28-04-2017 | 28-04-2017 | 4 |  | Quý
2.3.8.7 | Test “Tính độ liên kết giữa các câu” | 28-04-2017 | 28-04-2017 | 4
2.3.8.8 | Test “Tính độ ưu tiên giữa các câu tách ra” | 28-04-2017 | 28-04-2017 | 4 |  | Quý
2.3.8.9 | Test “Tạo node đồ thị” | 28-04-2017 | 28-04-2017 | 4 |  | Tân
2.3.8.10 | Test “Liên kết đồ thị” | 28-04-2017 | 28-04-2017 | 4 |  | Linh
3.2.9 | Fix bugs | 29-04-2017 | 2017-01-05 | 56
3.2.9.1 | Fix bugs of " Xem văn bản sau khi rút gọn " | 29-04-2017 | 29-04-2017 | 4 |  | Quý
3.2.9.2 | Fix bugs of “ Xuất văn bản sau khi rút gọn ” | 29-04-2017 | 29-04-2017 | 4 |  | Tân
3.2.9.3 | Fix bugs of “Tùy chỉnh kích thước rút gọn văn bản” | 29-04-2017 | 29-04-2017 | 4 |  | Tân
3.2.9.4 | Fix bugs of “ Xem đồ thị liên kết giữa các câu” | 30-04-2017 | 30-04-2017 | 4 |  | Tân
3.2.9.5 | Fix bugs of “ Xem tỉ lệ xếp hạng của các câu ” | 30-04-2017 | 30-04-2017 | 8 |  | Quý
3.2.9.6 | Fix bugs of “ Tìm kiếm nội dụng văn bản ” | 29-04-2017 | 30-04-2017 | 8 |  | Linh
3.2.9.7 | Fix bug of “Tính độ liên kết giữa các câu” | 2017-01-05 | 2017-01-05 | 8 |  | Linh
3.2.9.8 | Fix bug of “Tính độ ưu tiên giữa các câu tách ra” | 2017-01-05 | 2017-01-05 | 8 |  | Quý
3.2.9.9 | Fix bug of “Tạo node đồ thị” | 2017-01-05 | 2017-01-05 | 4 |  | Tân
3.2.9.10 | Fix bug of “Liên kết đồ thị” | 2017-01-05 | 2017-01-05 | 4 |  | Tân
3.2.10 | Re-testing | 2017-02-05 | 2017-03-05 | 42
3.2.10.1 | Re-test " Xem văn bản sau khi rút gọn " | 2017-02-05 | 2017-02-05 | 4 |  | Tân
3.2.10.2 | Re-test “ Xuất văn bản sau khi rút gọn ” | 2017-02-05 | 2017-02-05 | 4 |  | Quý
3.2.10.3 | Re-test “ Xem đồ thị liên kết giữa các câu ” | 2017-02-05 | 2017-02-05 | 6 |  | Linh
3.2.10.4 | Re-test “ Tùy chỉnh kích thước rút gọn văn bản ” | 2017-02-05 | 2017-02-05 | 4 |  | Quý
3.2.10.5 | Re-test “ Xem tỉ lệ xếp hạng của các câu ” | 2017-02-05 | 2017-02-05 | 4 |  | Tân
3.2.10.6 | Re-test “ Tìm kiếm nội dụng văn bản ” | 2017-02-05 | 2017-02-05 | 4 |  | Linh
3.2.10.7 | Test “Tính độ liên kết giữa các câu” | 2017-03-05 | 2017-03-05 | 4 |  | Linh
3.2.10.8 | Test “Tính độ ưu tiên giữa các câu tách ra” | 2017-03-05 | 2017-03-05 | 4 |  | Quý
3.2.10.9 | Test “Tạo node đồ thị” | 2017-03-05 | 2017-03-05 | 4 |  | Tân
3.2.10.10 | Test “Liên kết đồ thị” | 2017-03-05 | 2017-03-05 | 4 |  | Linh
3.2.12 | Release Sprint 2 | 2017-04-05 | 2017-05-05 | 16
3.2.12.1 | Sprint 2 Review Meeting | 2017-04-05 | 2017-04-05 | 8 |  | Tân, Quý, Linh
3.2.12.2 | Sprint 2 Retrospective | 2017-05-05 | 2017-05-05 | 8 |  | Tân, Quý, Linh
The total of working hour(s) |  |  |  |  | 626

## Sheet1 (hidden)
STT | Tên | Ngày bắt đầu | Ngày kết thúc | Thời gian ước tính | Tên thành viên
1 | Initial | 2016-08-01 | 2016-08-04 | 16
1.1 | Tổng hợp yêu cầu | 21-02-2017 | 2017-05-03 | 8 | Tân, Quý, Linh
1.2 | Viết tài liệu Proposal | 2017-07-03 | 2017-08-03 | 8 | Tân, Quý
2 | Start Up | 2017-08-03 | 17-03-2017 | 92
2.1 | Project’s Meeting | 2017-08-03 | 2017-08-23 | 8 | Tân, Quý, Linh
2.2 | Viết tài liệu User Stories | 2017-08-03 | 2017-10-03 | 24 | Tân, Quý, Linh
2.3 | Viết tài liệu Product Backlog | 2017-09-03 | 2017-10-03 | 12 | Tân, Quý, Linh
2.4 | Review Document | 2017-11-03 | 2017-11-03 | 8 | Tân, Quý, Linh
2.5 | Create Project Plan Document | 13-03-2017 | 15-03-2017 | 24 | Tân, Quý, Linh
2.6 | Review Document | 16-03-2017 | 2016-08-16 | 8 | Tân, Quý, Linh
2.8 | Review Document | 17-03-2017 | 17-03-2017 | 8 | Tân, Quý, Linh
3 | Development | 17-03-2017 | 2017-10-05
3.1 | Sprint 1 | 17-03-2017 | 2017-02-04 | 100
3.1.1 | Sprint Planning Meeting | 17-03-2017 | 17-03-2017 | 8 | Tân, Quý, Linh
3.1.2 | Tạo Sprint Backlog | 17-03-2017 | 17-03-2017 | 4 | Tân
3.1.3 | Tạo Test Plan document cho Sprint 1 | 18-03-2017 | 18-03-2017 | 4 | Linh
3.1.5 | Design user interface | 25-03-2017 | 26-03-2017 | 12
3.1.5.1 | Design user interface of “Nhập văn bản bằng tay” | 25-03-2017 | 25-03-2017 | 8 | Quý
3.1.5.2 | Design user interface of “Nhập văn bản từ file” | 26-03-2017 | 26-03-2017 | 4 | Linh
3.1.6 | Design Test case for: | 27-03-2017 | 27-03-2017 | 8
3.1.6.1 | Design test case cho chức năng “ Nhập văn bản bằng tay ” | 27-03-2017 | 27-03-2017 | 4 | Quý
3.1.6.2 | Design test case cho chức năng “ Nhập văn bản từ file ” | 27-02-2017 | 27-02-2017 | 4 | Linh
3.1.7 | Coding | 27-03-2017 | 28-03-2017 | 16
3.1.7.1 | Code chức năng “ Nhập văn bản bằng tay ” | 27-03-2017 | 28-03-2017 | 8 | Quý
3.1.7.2 | Code chức năng “Nhập văn bản từ file” | 27-03-2017 | 28-03-2017 | 8 | Linh
3.1.8 | Testing | 29-03-2017 | 29-03-2017 | 8
3.1.8.1 | Test “ Nhập văn bản bằng tay ” | 29-03-2017 | 29-03-2017 | 4 | Linh
3.1.8.2 | Test “ Nhập văn bản từ file ” | 29-03-2017 | 29-03-2017 | 4 | Tân
3.1.9 | Fix bugs | 30-03-2017 | 30-03-2017 | 16
3.1.9.1 | Fix bugs of “ Nhập văn bản bằng tay ” | 30-03-2017 | 30-03-2017 | 8 | Quý
3.1.9.2 | Fix bugs of “ Nhập văn bản từ file ” | 30-03-2017 | 30-03-2017 | 8 | Linh
3.1.10 | Re-testing | 31-03-2017 | 31-03-2017 | 8
3.1.10.1 | Re-test “Nhập văn bản bằng tay” | 31-03-2017 | 31-03-2017 | 4 | Linh
3.1.10.2 | Re-test “Nhập văn bản từ file” | 31-03-2017 | 31-03-2017 | 4 | Tân
3.1.11 | Release Sprint 1: | 2017-01-04 | 2017-02-04 | 16
3.1.11.1 | Sprint 1 Review Meeting | 2017-01-04 | 2017-01-04 | 8 | Tân, Quý, Linh
3.1.11.2 | Sprint 1 Retrospective | 2017-02-04 | 2017-02-04 | 8 | Tân, Quý, Linh
3.2 | Sprint 2 | 2017-07-04 | 2017-05-05 | 270
3.2.1 | Sprint Planning Meeting | 2017-07-04 | 2017-07-04 | 8 | Tân, Quý, Linh
3.2.2 | Tạo Sprint Backlog Document | 2017-07-04 | 2017-07-04 | 4 | Tân
3.2.3 | Tạo Test Plan document cho Sprint 2 | 2017-08-04 | 2017-08-04 | 8 | Tân
3.2.5 | Design User Interface | 13-04-2017 | 14-04-2017 | 24
3.2.5.1 | Design user interface "Xem văn bản sau khi rút gọn" | 13-04-2017 | 13-04-2017 | 4 | Linh
3.2.5.2 | Design user interface “Xuất văn bản sau khi rút gọn” | 13-04-2017 | 13-04-2017 | 4 | Quý
3.2.5.3 | Design user interface of "Xem đồ thị liên kết giữa các câu" | 13-04-2017 | 13-04-2017 | 4 | Tân
3.2.5.4 | Design user interface “ Tùy chỉnh kích thước rút gọn văn bản” | 14-04-2017 | 14-04-2017 | 4 | Tân
3.2.5.5 | Design user interface “Xem tỉ lệ xếp hạng của các câu” | 14-04-2017 | 14-04-2017 | 4 | Quý
3.2.5.6 | Design user interface “Tìm kiếm nội dụng văn bản” | 14-04-2017 | 14-04-2017 | 4 | Linh
3.2.6 | Design Test Case: | 15-04-2017 | 16-04-2017 | 24
3.2.6.1 | Design test case for " Xem văn bản sau khi rút gọn " | 15-04-2017 | 15-04-2017 | 4 | Linh
3.2.6.2 | Design test case for “Xuất văn bản sau khi rút gọn ” | 15-04-2017 | 15-04-2017 | 4 | Quý
3.2.6.3 | Design test case for “ Xem đồ thị liên kết giữa các câu ” | 15-04-2017 | 15-04-2017 | 4 | Tân
3.2.6.4 | Design test case for “ Tùy chỉnh kích thước rút gọn văn bản ” | 16-04-2017 | 16-04-2017 | 4 | Tân
3.2.6.5 | Design test case for “ Xem tỉ lệ xếp hạng của các câu ” | 16-04-2017 | 16-04-2017 | 4 | Quý
3.2.6.6 | Design test case for “ Tìm kiếm nội dụng văn bản ” | 16-04-2017 | 16-04-2017 | 4 | Linh
3.2.7 | Coding: | 17-04-2017 | 27-04-2017 | 84
3.2.7.1 | Code chức năng “ Xem văn bản sau khi rút gọn” | 17-04-2017 | 19-04-2017 | 12 | Linh
3.2.7.2 | Code chức năng “ Xuất văn bản sau khi rút gọn” | 17-04-2017 | 19-04-2017 | 12 | Quý
3.2.7.3 | Code chức năng “ Xem đồ thị liên kết giữa các câu” | 17-04-2017 | 21-04-2017 | 20 | Tân
3.2.7.4 | Code chức năng “ Tùy chỉnh kích thước rút gọn văn bản ” | 22-04-2017 | 27-04-2017 | 12 | Tân
3.2.7.5 | Code chức năng “ Xem tỉ lệ xếp hạng của các câu ” | 20-04-2017 | 27-04-2017 | 16 | Quý
3.2.7.6 | Code chức năng “ Tìm kiếm nội dụng văn bản” | 20-04-2017 | 27-04-2017 | 12 | Linh
3.2.8 | Testing: | 28-04-2017 | 28-04-2017 | 28
3.2.8.1 | Test " Xem văn bản sau khi rút gọn " | 28-04-2017 | 28-04-2017 | 4 | Quý
3.2.8.2 | Test “ Xuất văn bản sau khi rút gọn ” | 28-04-2017 | 28-04-2017 | 4 | Tân
3.2.8.3 | Test “ Xem đồ thị liên kết giữa các câu ” | 28-04-2017 | 28-04-2017 | 8 | Linh,Quý
3.2.8.4 | Test “ Tùy chỉnh kích thước rút gọn văn bản ” | 28-04-2017 | 28-04-2017 | 4 | Linh
3.2.8.5 | Test “ Xem tỉ lệ xếp hạng của các câu ” | 28-04-2017 | 28-04-2017 | 4 | Tân
3.2.8.6 | Test “ Tìm kiếm nội dụng văn bản ” | 28-04-2017 | 28-04-2017 | 4 | Quý
3.2.9 | Fix bugs | 29-04-2017 | 2017-01-05 | 48
3.2.9.1 | Fix bugs of " Xem văn bản sau khi rút gọn " | 29-04-2017 | 30-04-2017 | 8 | Linh
3.2.9.2 | Fix bugs of “ Xuất văn bản sau khi rút gọn ” | 29-04-2017 | 30-04-2017 | 8 | Quý
3.2.9.3 | Fix bugs of “ Xem đồ thị liên kết giữa các câu ” | 29-04-2017 | 2017-01-05 | 16 | Tân
3.2.9.4 | Fix bugs of “ Tùy chỉnh kích thước rút gọn văn bản ” | 29-04-2017 | 30-04-2017 | 8 | Linh
3.2.9.5 | Fix bugs of “ Xem tỉ lệ xếp hạng của các câu ” | 2017-01-05 | 2017-01-05 | 4 | Quý
3.2.9.6 | Fix bugs of “ Tìm kiếm nội dụng văn bản ” | 2017-01-05 | 2017-01-05 | 4 | Linh
3.2.10 | Re-testing | 2017-02-05 | 2017-02-05 | 26
3.2.10.1 | Re-test " Xem văn bản sau khi rút gọn " | 2017-02-05 | 2017-02-05 | 4 | Tân
3.2.10.2 | Re-test “ Xuất văn bản sau khi rút gọn ” | 2017-02-05 | 2017-02-05 | 4 | Quý
3.2.10.3 | Re-test “ Xem đồ thị liên kết giữa các câu ” | 2017-02-05 | 2017-02-05 | 6 | Linh
3.2.10.4 | Re-test “ Tùy chỉnh kích thước rút gọn văn bản ” | 2017-02-05 | 2017-02-05 | 4 | Quý
3.2.10.5 | Re-test “ Xem tỉ lệ xếp hạng của các câu ” | 2017-02-05 | 2017-02-05 | 4 | Tân
3.2.10.6 | Re-test “ Tìm kiếm nội dụng văn bản ” | 2017-02-05 | 2017-02-05 | 4 | Linh
3.2.12 | Release Sprint 2 | 2017-03-05 | 2017-04-05 | 16
3.2.12.1 | Sprint 2 Review Meeting | 2017-03-05 | 2017-03-05 | 8 | Tân, Quý, Linh
3.2.12.2 | Sprint 2 Retrospective | 2017-04-05 | 2017-04-05 | 8 | Tân, Quý, Linh
The total of working hour(s) |  |  |  | 468 hours